# ConvoAI Project

## Work Breakdown Structure (WBS)

6-Week MVP Development Project

## Executive Summary

This Work Breakdown Structure outlines all tasks required to complete the ConvoAI MVP within a 6-week timeline. The project is divided into 3 major sprints with realistic scope for a 3-person team balancing other commitments.

The structure is designed for approximately 12-15 hours per person per sprint (36-45 hours total per sprint, 108-135 hours total project). Each task is assigned to a specific role with estimated durations and dependencies clearly identified.

# Sprint 1: Foundation & Infrastructure (Weeks 1-2)

## 1.1 Project Planning

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 1.1.1 | Conduct team kickoff meeting | All Team | 1.5 hours |
| 1.1.2 | Define roles and responsibilities | All Team | 1 hour |
| 1.1.3 | Create project schedule and milestones | Full-Stack | 3 hours |
| 1.1.4 | Set up Trello board with task tracking | Full-Stack | 1.5 hours |

## 1.2 Development Environment Setup

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 1.2.1 | Set up GitHub repository with branching strategy | Backend | 2 hours |
| 1.2.2 | Configure Git workflow (feature branches, PRs) | Backend | 1.5 hours |
| 1.2.3 | Set up local development environments (Node.js, PostgreSQL) | All Team | 3 hours |
| 1.2.4 | Create .env.example templates for environment variables | Backend | 1 hour |

## 1.3 Technology Stack Setup

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 1.3.1 | Initialize React application with Vite | Frontend | 2 hours |
| 1.3.2 | Set up basic CSS and styling | Frontend | 2 hours |
| 1.3.3 | Initialize Node.js/Express backend project | Backend | 2 hours |
| 1.3.4 | Set up PostgreSQL database locally | Backend | 2.5 hours |
| 1.3.5 | Configure Prisma ORM and create initial schema | Backend | 4 hours |

## 1.4 Basic UI Structure

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 1.4.1 | Set up React Router with basic routes | Frontend | 2 hours |
| 1.4.2 | Create basic layout components | Frontend | 3 hours |
| 1.4.3 | Build landing page | Frontend | 2 hours |

# Sprint 2: Core Features Development (Weeks 3-4)

## 2.1 Database Schema Design

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 2.1.1 | Design users table schema | Backend | 2 hours |
| 2.1.2 | Create and run database migrations | Backend | 2 hours |
| 2.1.3 | Create restaurant scenario content | Full-Stack | 2 hours |

## 2.2 Authentication System - Backend

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 2.2.1 | Implement user registration endpoint with bcrypt | Backend | 4 hours |
| 2.2.2 | Implement login endpoint with JWT token generation | Backend | 3 hours |
| 2.2.3 | Create JWT verification middleware | Backend | 3 hours |
| 2.2.4 | Test authentication endpoints | Backend | 2 hours |

## 2.3 Authentication System - Frontend

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 2.3.1 | Create registration page with form | Frontend | 4 hours |
| 2.3.2 | Create login page with form | Frontend | 3 hours |
| 2.3.3 | Implement client-side authentication state management | Frontend | 4 hours |
| 2.3.4 | Add protected route functionality | Frontend | 2 hours |
| 2.3.5 | Test authentication flow end-to-end | All Team | 2 hours |

## 2.4 AI Integration

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 2.4.1 | Create Hugging Face account and get free API token | Backend | 30 min |
| 2.4.2 | Test Mistral-7B model for Spanish conversation quality | Backend | 2 hours |
| 2.4.3 | Create AI service wrapper for API calls | Backend | 4 hours |
| 2.4.4 | Design system prompt template for restaurant scenario | Backend | 3 hours |
| 2.4.5 | Create conversation endpoint (send/receive messages) | Backend | 4 hours |
| 2.4.6 | Test basic AI conversation flow | Backend | 2 hours |

# Sprint 3: Chat Interface & Deployment (Weeks 5-6)

## 3.1 Chat Interface

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 3.1.1 | Design chat UI layout | Frontend | 3 hours |
| 3.1.2 | Build message bubble components | Frontend | 3 hours |
| 3.1.3 | Create chat input component with send functionality | Frontend | 3 hours |
| 3.1.4 | Implement auto-scroll and loading states | Frontend | 2 hours |
| 3.1.5 | Connect chat UI to backend API | Frontend | 4 hours |
| 3.1.6 | Style chat interface with CSS | Frontend | 3 hours |

## 3.2 Testing & QA

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 3.2.1 | Test all user flows end-to-end | All Team | 2 hours |
| 3.2.2 | Test on Chrome, Firefox, Safari | Frontend | 2 hours |
| 3.2.3 | Test responsive design on mobile devices | Frontend | 2 hours |
| 3.2.4 | Fix critical bugs (P0/P1) | All Team | 5 hours |

## 3.3 Deployment

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 3.3.1 | Set up Vercel for frontend deployment | Full-Stack | 2.5 hours |
| 3.3.2 | Set up Railway/Render for backend + PostgreSQL | Backend | 3 hours |
| 3.3.3 | Configure production environment variables | Backend | 1.5 hours |
| 3.3.4 | Run database migrations in production | Backend | 1 hour |
| 3.3.5 | Deploy and test production environment | All Team | 3 hours |

## 3.4 Documentation & Presentation

| # | Task | Owner | Duration |
| --- | --- | --- | --- |
| 3.4.1 | Write README with setup instructions | Full-Stack | 2 hours |
| 3.4.2 | Create user guide documentation | Full-Stack | 1.5 hours |
| 3.4.3 | Prepare demo presentation slides | All Team | 3 hours |
| 3.4.4 | Test with 10-15 external users for feedback | All Team | 2 hours |

# Project Summary

| Total Sprints | 3 |
| --- | --- |
| Total Duration | 6 weeks |
| Team Size | 3 developers |
| Estimated Time | 108-135 hours total (36-45 hours per person) |
| Hours Per Week | ~6-7.5 hours per person |

## Key Milestones

| # | Milestone | Owner | Timeline |
| --- | --- | --- | --- |
| M1 | Development Environment Setup Complete | All Team | Week 2 |
| M2 | Authentication & AI Integration Ready | All Team | Week 4 |
| M3 | Full Application Deployed | All Team | Week 6 |

## Time Breakdown by Sprint

| Sprint | Total Hours | Hours Per Person |
| --- | --- | --- |
| Sprint 1 | 36-40 hours | 12-13 hours |
| Sprint 2 | 38-45 hours | 13-15 hours |
| Sprint 3 | 34-40 hours | 11-13 hours |
| TOTAL | 108-125 hours | 36-42 hours |

ConvoAI Project Team

February 2026